N6Cam People-Counter Firmware

Milestone Plan & Cost Proposal

| Project | N6Cam People-Counter Firmware |
| --- | --- |
| Vendor | Kamacode Ltd. |
| Client | ITP / Novex |
| Reference SOW | SOW — N6Cam People-Counter Firmware (2026-04-24) |
| Document | Milestone Plan & Cost Proposal |
| Date | 2026-04-26 |
| Prepared by | Ilan Ganor |
| Status | Draft for client approval |

# 1. Overview

This proposal covers the design, implementation, and delivery of custom application firmware for the SIANA N6Cam Edge AI Sensing Kit, per the SOW dated 2026-04-24. Scope is firmware only; mechanical, optical, and power design are out of scope, as is the SIANA hardware quote.

The work is structured into five sequential milestones. Each milestone produces a self-contained, independently acceptable deliverable. Payment is triggered on acceptance of each milestone's deliverables.

# 2. Scope Summary

- FR-1 — People detection and count tracking with configurable debounce and inference rate.

- FR-2 — Image capture on every debounced count-change event.

- FR-3 — Event logging to SD card (timestamped images plus append-only event log).

- FR-4 — Event-out GPIO pulse on every logged event.

- FR-5 — SD-card interlock input with RAM-buffered events, clean unmount/remount, and overflow accounting.

- FR-6 — Firmware update over UART with bootloader, integrity check, and A/B or golden-image fallback.

- Acceptance: bench-executable test procedure including a ≥ 24 h soak.

# 3. Milestones, Effort & Cost

All effort estimates assume the open questions in SOW §5 are resolved during M1. Material changes to those answers (for example, a custom detection model in place of the stock SIANA model, or signed-image update with on-device key provisioning) will be handled as a written change request before affecting downstream milestones.

| # | Milestone | Scope & Deliverables | Payment % |
| --- | --- | --- | --- |
| M1 | Kickoff & Design Review | Resolve all open questions in §5 of the SOW (detection model, image pipeline, GPIO assignments, SD filesystem behavior, RAM budget, UART arbitration, update security, time source, power loss). Deliver: architecture & design document, GPIO/electrical pinout, event-log file format, SD directory layout, UART update protocol spec. Signed-off design baseline before implementation starts. | 20 % |
| M2 | Detection, Capture & SD Logging (FR-1, FR-2, FR-3) | On-device person-detection inference on live camera stream, instantaneous count tracking with configurable debounce, still-frame capture on debounced count-change events, append-only event log (JSONL or CSV) plus timestamped image files on SD card. Build-time configurable inference rate, image format/quality, and log layout. | 25 % |
| M3 | Event GPIO & SD-Card Interlock (FR-4, FR-5) | Configurable event-out GPIO pulse on every logged event. Interlock input GPIO with debounce, in-flight write completion, clean filesystem flush/unmount, bounded RAM FIFO for events while interlock is asserted, ordered drain on re-mount, overflow accounting (drop policy + counter logged on resume). Optional “safe to remove” ACK output. | 25 % |
| M4 | UART Firmware Update (FR-6) | Bootloader / resident update agent, image reception over UART (XMODEM/YMODEM or agreed protocol), CRC32 integrity check (signed-image option per design review), A/B or golden-image fallback so an interrupted update cannot brick the device, host-side Linux CLI flasher, documented protocol, configurable baud (≥ 115200). | 20 % |
| M5 | Integration, Acceptance & Release | Execution of the bench acceptance test procedure (count-change accuracy, 1-pulse-per-event verification, interlock buffer/overflow scenarios, interrupted-update recovery, ≥ 24 h soak). Final integration document, release FW binary (signed if applicable), bootloader binary, host flasher utility, build/toolchain instructions, known-issues note. | 10 % |
|  | Total | Sum of milestone payments equals the fixed project total in §4. | 100 % |

# 4. Commercial Summary

| Total effort | 300 hours |
| --- | --- |
| Hourly rate | 275 NIS / hour |
| Project total (excl. VAT) | ₪ 82,500 |
| Currency | NIS (Israeli New Shekel) |
| Payment schedule | Milestone-based, per the percentages in the table in §3 |
| Payment trigger | On deliverable acceptance, per milestone |
| Payment terms | Net-30 from invoice date |

# 5. Assumptions and Exclusions

## 5.1 Assumptions

- SIANA N6Cam hardware, BSP, and base SDK are provided in working condition by ITP / Novex.

- The stock SIANA person-detection model is reused. Training or sourcing a custom model is out of scope.

- FAT32 is acceptable for the SD-card filesystem. The on-device driver supports clean unmount.

- At least one UART is available for the update path. Update-mode entry mechanism (magic sequence, GPIO strap, or command) is agreed during M1.

- Available free GPIOs for the event-out and interlock-in signals are confirmed during M1.

- Time source: monotonic timestamps are acceptable in the absence of an RTC; external time-set hook is provided if needed.

- CRC32 image integrity is the baseline for FR-6. Code-signing with on-device public key is an option to be confirmed in M1; if selected, key provisioning effort is included in M4.

- ITP / Novex provides hardware units (N6Cam plus an SD-card test fixture) and timely access to a technical point of contact.

## 5.2 Exclusions

- SIANA hardware, optics, mechanical enclosure, and power design.

- Production programming, manufacturing-line bring-up, and field rollout.

- Regulatory or EMC compliance work.

- Cloud, server, or back-office integration of the event log.

- Training of an end-user-specific detection model.

- On-site support outside of remote acceptance review.

# 6. Schedule

Indicative duration is approximately 10 to 12 calendar weeks from kickoff to M5 acceptance, assuming hardware availability at M1 and a single-track engagement. A detailed timeline with target dates is fixed at M1 sign-off.

# 7. Change Control

Any change to scope, deliverables, GPIO assignments, update-mode security model, or detection model that materially affects effort is documented in a change request signed by both parties before work proceeds. Effort and cost are adjusted at the agreed hourly rate.

# 8. Authorization

Acceptance of this proposal authorizes Kamacode Ltd. to begin Milestone 1. Signature below constitutes agreement to the scope, milestones, effort, rate, and commercial terms set out in this document.

| For Kamacode Ltd. Ilan Ganor, CEO Signature / Date | For ITP / Novex Name / Title Signature / Date |
| --- | --- |